## Tool
Instructions
1 | Build your list of project deliverables in the Deliverables List by Practice/Activity colunm by selecting each occurance of a Practice/Activities on a row that will be completed during your project and write a description of the deliverable.
2 | Note the order, 1, 2, 3, etc, in the Order of Completion column, each Practive/Activity -Deliverable will be completed over the term of the project.
Sort the List (Deliverables list by Practice/Activity, Description and Order of Completion) by the Order of Completion column, lowest to highest.
3 | Group practices and activites list, starting at the top of the list (beginning of the project) , that are complementary and logical to complete at the same time by asign them a number beginning with 1, next group 2 and so on (Group #). Sort the List by Group #
Review your Groups of Pactices/Activities. Does the Group illustrate the completion of a Project Phase/Milestone? If yes, you have the Practices/Activites assigned to write an objective. If no, assess, reorder and resort as needed.
4 | Draft an objective statement that summarizes the completion of these practices and activities. Repeat until you have completed each Group #. If the Group # still illustrates the order of completion of the objectives, The Group# is your Objective #. If not, number them in order of completion to get your Objective #.
1 |  | 2 | 3 | 4
Deliverables List by Practice/Activity | Description | Order of Completion | Group # | Objective Statement

## Example
Project Goal: | The residents of A, B and C neighborhoods are educated on the benefits of the urban forest to their community, engaged in their planting and care, and participated in the planting of 400 trees on private property.
Deliverables List by Practice/Activity | Description | Order of Completion | Group # | Draft Objective Statement
Outreach Products | Outreach postcard | 1 | 1 | The outreach postcard and postplanting care instructions, the property owner paper and website applications and the selection process, and the property owner agreements required to implement the program are developed and published by the end of Quarter 1.
Education/Training Products | Post planting care instructions fact sheet fo property owners ( POs) | 2 | 1
Event Registration | PO application for tree planting and selection criteria | 3 | 1
Outreach Products | Website tree planting application | 4 | 1
Event Registration | PO tree planting agreement | 5 | 1
Outreach Event | Door to door canvasing (Date of event & post cards distributed) | 6 | 2 | Outreach products will be delivered in person to 500 residents and 3 neighborhood meetings will be attended to promote the program and solicit tree planting applications by the end of Quarter 1
Outreach Event | Attend 3 Neighborhood meetings ( Date & event) | 7 | 2
Event Registration | Select applicants for fall planting (Applicant list and selections) | 8 | 3 | Fall tree planting applicants will be selected, planting sites will be inventoried and tree species for planting will be selected, and PO agreements will be secured by the end of quarter 2
Partial Tree Inventory | Inventory planting sites (planting site inventory list) | 9 | 3
Practice Plans | Select tree species for planting (Planting site inventory with species slection list) | 10 | 3
Event Registration | Secure PO agreements (Copies of agreements) | 11 | 3
Tree Planting | Complete Fall tree planting. (Complted tree planting and tool/instructions delivery list) | 12 | 4 | Fall tree planting preparation, tree planting, and the distribution of tree mainteance tools and instructions to the POs will be completed by Quarter 2
Event Registration | Select applicants for fall planting (Applicant list and selections) | 13 | 5 | Winter tree planting applicants will be selected, planting sites will be inventoried and tree species will be selected, and PO agreements will be secured by the end of Quarter 2
Partial Tree Inventory | Inventory planting sites (planting site inventory list) | 14 | 5
Practice Plans | Select tree species for planting (Planting site inventory with species slection list) | 15 | 5
Event Registration | Secure PO agreements (Copies of agreements) | 16 | 5
Tree Planting | Complete spring tree planting.( Location of planting, species planted and date.) | 17 | 6 | Winter tree planting preparation, tree planting, and the distribution of tree mainteance tools and instructions to the POs will be completed by the end of Quarter 3
Tree Maintenance | Complete tree watering. (List of sites watered and dates.) | 18 | 7 | Contract watering of all tree plantings will begin in the 3rd quarter and conclude at the end of Quarter 4.

## DDs & Defintions
Advocacy Group Development | Organization Strategic Plan Development | Fees for professional planning firm to facilitate and publish a strategic plan.
Education & Training
Programs | Education/Training Program Plan | Development of education or training program.
| Volunteer Stewardship Program Plan | Development of a long-term, sustainable community volunteer U&CF stewardship program.
| Workforce Development Program Plan | Development of a long-term, sustainable urban and community forestry job training program.
Practices & Activities | Education/Training Products | Training and educational publications and media products.
| Education/Training Event | Development and delivery of educational or training event.
| Education/Training Tools | PPE and tools required to complete the education or training event or program.
| Professional Certifications | Attend training and acquire a U&CF professional credential.
Inventories & Assessments | Tree Canopy Cover Assessment | A tree canopy cover assessment uses aerial photographs and other types of remote sensing data to quantify the area of a community covered by tree canopy, vegetation, hardscape and other land cover features for planning purposes. The assessment also quantifies the ecosystem services provided by the tree canopy.
| Urban Heat Island Assessment | Assessment and analysis using remote sensing data and on the ground surveys will identify UHI areas from which mitigation strategies such as tree planting can be developed.
| Program Assessment/Review | A formal review of an organization or program policies and practices to identify opportunities for organizational design improvement.
| Complete Tree Inventory | An inventory of all trees and planting sites located on community street right-of-ways and/or community properties.
| Partial Tree Inventory | A partial tree inventory records trees or sites that meet a specific management objective. Examples include a risk tree inventory, tree planting site inventory or an inventory of trees with forest health issue.
| Project Tree Inventory | An inventory of all trees located within a project area.
| Sample Tree Inventory | A statistically valid sample inventory of trees in a community or defined area in the community. The resulting data will provide estimates of numbers of trees, tree species, condition, age and management needs for planning purposes.
| Stakeholder Survey | Surveys of stakeholders to solicit comment and or identify issues and needs for strategic planning and implementation.
| Tree Inventory Tools | Computer software to house, maintain and manage a tree inventory. Data collection devices and other tree inventory tools.
Outreach | Outreach Program | Development of outreach program.
| Outreach Event | Development and delivery of an outreach event.
| Outreach Products | Outreach publications and media products.
| Stakeholder Survey | Surveys of stakeholders to learn urban and community forestry knowledge, needs and/or engage in an outreach, educational or training event.
Ordinances, Policy, Standards & Specifications | Conservation Development Ordinance | An ordinance that directs tree and other natural resource conservation during development.
| Historic/Legacy Tree Ordinance | An ordinance that provides protection for individual trees of historical significance.
| Landscaping Ordinance | An ordinance that specifies landscaping requirements for existing properties or properties under development.
| Public Tree Ordinance | An ordinance that establishes municipal authority over the management of public trees and sets management policy and standards. All Tree City USA communities or communities working toward Tree City USA status must have a public tree ordinance.
| Urban Forestry Standards and Specifications Document | Policy, standards, and specifications document to guide and the planting, maintenance, removal and protection of community trees.
Plans | Community Forestry Plan | A plan that guides the development and implementation of community wide or specific community forestry activities.
| Practice Plan | A plan that establishes objectives, specifications, policy and a budget that addresses a single urban forestry practice in the management of the community's urban forest. The primary audience is the staff and leadership of the organization. Examples include food forest plan, a risk tree mitigation plan, a tree maintenance plan, a tree planting and post-care plan or an urban wood utilization plan.
| Management Plan | A comprehensive plan that establishes policies, goals, objectives and a budget for the operational management of the community's urban forest. The primary audience is the staff and leadership of the organization.
| U&CF Comprehensive Plan | A comprehensive plan that establishes policies, goals, and objectives for all U&CF activities for the management of the community's urban forest. The audience is the public, staff, and leadership of the community.
Tree Maintenance | Tree Maintenance | Completion of a tree maintenance project; watering, pruning, removal etc.
| Tree Maintenance Tools | Pruners, saws and other arboricultural diagnostic and maintenance tools and equipment.
Tree Planting | Tree Planting | Completion of the tree planting.
| Tree Planting Site Preparation | Removal of poor soil, asphalt or concrete to establish suitable growing conditions for the species of tree to be planted.
| Tree Planting Tools and Supplies | Tools, mulch, staking supplies and watering bags.